## SWMS Checklist
Document ID: MISAFE-IMS-TMP-022-V1.0
SAFE WORK METHOD STATEMENT (SWMS) — REVIEW CHECKLIST
Company / Organisation:
Project / Site / Business Unit:
SWMS Reference / Task:
Reviewed By: |  | Review Date: |  | Review Outcome:
Ref | Checklist Item | Regulatory Requirement / Guidance | Compliant (Y / N / P) | N/A | Evidence / Notes
1. DOCUMENT CONTROL & IDENTIFICATION
1.1 | SWMS has a unique document reference number | Required for version control and traceability. Aligns with ISO 9001 Cl. 7.5 and WHS Regulations 2011 s.299.
1.2 | Document title clearly identifies the high-risk construction work (HRCW) task | Must reflect the specific task as listed under WHS Regulation 2011 s.291 HRCW categories.
1.3 | Version number and date of issue are recorded | Ensures only current version is in use on site. Required under ISO 45001 Cl. 7.5.2.
1.4 | Document owner / author is identified | Accountability for document maintenance and accuracy.
1.5 | SWMS status is indicated (e.g. Draft, Approved, Superseded) | Prevents use of outdated versions. Aligns with ISO 9001 document control requirements.
1.6 | Uncontrolled copy notice is present where applicable | Notifies users that printed copies may not reflect current approved version.
2. SCOPE OF WORK & SITE DETAILS
2.1 | High-risk construction work (HRCW) category is clearly identified | WHS Regulation 2011 (Cth/Qld/NSW/VIC/SA/WA) s.291 — SWMS is required for all HRCW activities.
2.2 | Project name, site address and location details are recorded | Required for site-specific application of controls.
2.3 | Principal Contractor (PC) details are included where applicable | WHS Regulation 2011 s.293 — PC must be notified and SWMS provided before work commences.
2.4 | Subcontractor / performing organisation is identified | Establishes accountability for the work being performed.
2.5 | Scope of work is clearly described including task boundaries | Prevents scope creep; ensures workers understand limits of the SWMS coverage.
2.6 | Plant, equipment and materials to be used are listed | Enables pre-work inspection, confirms fitness for purpose under WHS Regs.
3. LEGISLATIVE & REGULATORY COMPLIANCE
3.1 | Applicable WHS/OHS legislation is referenced | SWMS must reflect obligations under the relevant State/Territory WHS Act and Regulations.
3.2 | Relevant Codes of Practice are referenced | E.g. Safe Work Australia Codes — Managing Risks in Construction; Silica Dust Management; Working at Heights; etc.
3.3 | Applicable Australian Standards are referenced | E.g. AS/NZS 1576 (scaffolding), AS/NZS 1891 (fall arrest), AS 2550 (cranes), AS 4024 (guarding), etc.
3.4 | Notifiable work requirements have been considered | WHS Regulation s.291 HRCW requires SWMS. Confirm notification obligations to regulator where applicable.
3.5 | SWMS has been prepared before the HRCW commences | WHS Regulation 2011 s.299 — SWMS must be prepared prior to commencement of HRCW.
3.6 | Silica dust risk obligations addressed where relevant | Model WHS Regulations s.50A (2024) — mandatory air monitoring, health monitoring, and controls for crystalline silica.
4. HAZARD IDENTIFICATION
4.1 | All significant hazards associated with the task are identified | WHS Regulation 2011 s.299(3)(a) — must identify work, hazards and risks before listing controls.
4.2 | Hazards are identified for each step / work sequence | Step-by-step hazard identification improves control specificity and practicality.
4.3 | Environmental hazards are included (e.g. weather, terrain, ground conditions) | Site-specific hazards must be captured; generic SWMS must be site-reviewed.
4.4 | Biological and chemical hazards are identified where applicable | Includes asbestos, silica, lead, hazardous chemicals; refer to SDS/MSDS as required.
4.5 | Hazards to third parties and the public are considered | Duty of care extends beyond workers — WHS Act s.19.
4.6 | Hazards arising from plant and equipment are identified | Plant registration, inspection, and hazard controls required under WHS Regulation s.209.
5. RISK ASSESSMENT
5.1 | Initial (inherent) risk rating is assessed for each hazard | Risk rating must reflect likelihood and consequence without controls applied.
5.2 | Risk rating methodology is consistent (e.g. 5x5 matrix or equivalent) | Consistent methodology ensures objective and comparable assessments.
5.3 | Residual (controlled) risk rating is assessed after controls | Demonstrates the effectiveness of proposed controls in reducing risk.
5.4 | Risk ratings are documented in the SWMS | WHS Regulation s.299 — risks arising from the work must be documented.
5.5 | Risks are assessed in the context of the specific site / task | Generic risk ratings are insufficient; must reflect actual site conditions and task specifics.
5.6 | Adequacy of controls is confirmed before approving the SWMS | Residual risk must be reduced to as low as reasonably practicable (ALARP) per WHS Act s.18.
6. CONTROL MEASURES — HIERARCHY OF CONTROLS
6.1 | Elimination has been considered as the first control option | WHS Act s.17 — duty to eliminate risk so far as is reasonably practicable.
6.2 | Substitution controls are documented where elimination is not reasonably practicable | E.g. substitute hazardous material with lower-risk alternative; use lower-voltage equipment.
6.3 | Isolation controls are specified where applicable | E.g. barricading, exclusion zones, lock-out/tag-out (LOTO) procedures.
6.4 | Engineering controls are included before administrative/PPE measures | Hierarchy of controls (WHS Reg s.36) — engineering controls ranked above administrative and PPE.
6.5 | Administrative controls are clearly described | Includes training, supervision, safe work procedures, permits, inductions, signage, communication.
6.6 | Personal Protective Equipment (PPE) is specified last in the hierarchy | PPE is a lower-order control — must not be the primary or sole control for significant risks.
6.7 | PPE specified is appropriate to the hazard and task | Must reference applicable standards (e.g. AS/NZS 1337, AS/NZS 1715/1716, AS/NZS 4602).
6.8 | Controls are specific, practical and implementable on site | Vague controls (e.g. 'take care') are not compliant. Controls must be actionable and verifiable.
7. WORK SEQUENCE / STEP-BY-STEP METHOD
7.1 | Work is broken down into logical, sequential steps | Step-by-step structure enables consistent task execution and simplifies worker instruction.
7.2 | Each step identifies associated hazards, risks and controls | Aligns with WHS Regulation s.299(3) — step-by-step linkage of hazard-risk-control is required.
7.3 | Work sequence is realistic and reflects how work is actually performed | SWMS must not be theoretical — it must reflect actual site practice.
7.4 | Critical steps are clearly emphasised | Ensures workers understand where the highest risk occurs in the task sequence.
7.5 | Emergency and incident response steps are included in the sequence | Enables immediate action if something goes wrong mid-task.
8. TRAINING, COMPETENCY & LICENCING
8.1 | Required qualifications, licences and competencies are identified | E.g. High Risk Work licences (WHS Reg s.61), forklift, scaffolding, dogging, rigging, EWP.
8.2 | Training requirements specific to the task are documented | Includes task-specific induction, equipment operation, hazardous substance handling.
8.3 | Supervisor / responsible person competency is confirmed | Competent person (WHS Regulation s.9) must be designated for HRCW.
8.4 | Workers have been briefed on the SWMS prior to commencing work | WHS Regulation s.299(3)(f) — workers must be consulted and must understand the SWMS.
8.5 | Verification of worker understanding is recorded | E.g. toolbox talk record, sign-on, pre-start checklist, verbal confirmation noted.
9. CONSULTATION & WORKER SIGN-OFF
9.1 | Workers involved in the task were consulted in developing the SWMS | WHS Act s.47 and WHS Regulation s.299(2) — workers must be involved in SWMS preparation.
9.2 | Health and Safety Representatives (HSRs) were consulted where applicable | WHS Act s.68 — HSRs have a right to be consulted on matters affecting worker safety.
9.3 | All workers performing the task have read and signed the SWMS | WHS Regulation s.299(3)(f) — signed acknowledgement is a regulatory requirement.
9.4 | Sign-off section captures name, signature, date and role | Must be legible and auditable; digital signatures are acceptable if system records are maintained.
9.5 | A mechanism exists for workers to raise concerns about the SWMS | WHS Act s.47 — workers have the right to raise issues; SWMS should include a process for this.
9.6 | New workers inducted and signed onto the SWMS before commencing | SWMS coverage must extend to all workers regardless of when they join the task.
10. APPROVAL & AUTHORISATION
10.1 | SWMS has been reviewed by a competent person prior to approval | Competent person review ensures technical accuracy and adequacy of controls.
10.2 | SWMS is approved by the Principal Contractor or authorised person | WHS Regulation s.293 — PC must ensure SWMS is prepared and must receive a copy.
10.3 | Approval date is recorded on the document | Required for version control and to confirm SWMS was approved before work commenced.
10.4 | Approval section includes name, role, signature and date | Establishes clear accountability for the approved version.
10.5 | SWMS has been provided to the Principal Contractor before work commences | WHS Regulation s.299(3)(e) — contractor must give PC copy of SWMS before HRCW begins.
11. MONITORING, REVIEW & REVISION
11.1 | SWMS review triggers are defined (e.g. incident, near-miss, change in scope) | WHS Regulation s.299(4) — SWMS must be reviewed and revised if it ceases to be adequate.
11.2 | Procedure for updating the SWMS mid-task is documented | Work must stop if conditions change materially and the SWMS is no longer adequate.
11.3 | SWMS has been reviewed following any incident or near miss | Post-incident review is a regulatory expectation and best practice under ISO 45001 Cl. 10.2.
11.4 | SWMS is reviewed periodically even if no incident occurs | Routine review ensures controls remain current with legislation, standards and site conditions.
11.5 | Change history / revision log is maintained | Supports version control and demonstrates ongoing management of the document.
12. EMERGENCY RESPONSE
12.1 | Emergency contacts and procedures are included in the SWMS | Workers must know what to do in an emergency — aligns with WHS Regulation s.43.
12.2 | First aid resources and location are identified | WHS Regulation s.42 — first aid must be accessible; location must be known to workers.
12.3 | Muster points and evacuation procedures are referenced | Site-specific emergency response plan must be accessible and referenced in the SWMS.
12.4 | Spill, overexposure and hazardous substance incident responses are included where applicable | Required for any SWMS involving hazardous chemicals, silica, lead or other regulated substances.
12.5 | Emergency stop and isolation procedures for plant are included | Critical for tasks involving plant, machinery or powered equipment.
13. SPECIFIC HRCW REQUIREMENTS
13.1 | Working at heights — fall prevention hierarchy applied (WHS Reg s.291(1)(d)) | Fall prevention, passive fall arrest, work positioning, then fall arrest — in that order.
13.2 | Confined space — entry permits, atmospheric testing, rescue plan included | WHS Regulation Part 4.3 — confined space entry has specific and strict requirements.
13.3 | Excavation / trenching — shoring, benching or battering controls specified | WHS Regulation s.306W — excavation over 1.5m requires specific controls.
13.4 | Demolition — engineer's report, asbestos register check, sequencing plan referenced | Demolition work requires specific planning; asbestos must be identified before demolition begins.
13.5 | Crane / lifting operations — lift plan, rated capacity, exclusion zones, dogger details | WHS Regulation Part 5.1 — plant registration, inspection and crane/rigging licence required.
13.6 | Silica-generating work — LEV, water suppression, air monitoring, health monitoring | Model WHS Regulations 2024 amendments s.50A — mandatory controls for crystalline silica work.
13.7 | Electrical work — isolation verified, testing completed, permit to work referenced | AS/NZS 3000 and Electrical Safety Act obligations apply; must be performed by licenced electrician.
13.8 | Hot work — fire watch, fire suppression available, permit to work in place | Permit to work system required for hot work in areas where flammable materials are present.
REVIEW SUMMARY
Overall Compliance Rating:
Non-Compliances Identified:
Corrective Actions Required:
SWMS Approved for Use:
Reviewer Comments:
Uncontrolled When Printed |  |  |  | Copyright © MiSAFE Solutions Pty Ltd

## Instructions
SWMS CHECKLIST — FIELD GUIDE
Field | Guidance Notes
Ref | Unique item reference number for each checklist line. Use when logging non-compliances or corrective actions.
Checklist Item | The specific compliance criterion being assessed. Each item is derived from WHS legislation, Australian Standards, Codes of Practice or regulatory guidance.
Regulatory Requirement / Guidance | The legislative basis or best-practice reference for the criterion. Reviewer should confirm current legislation applies in the relevant State or Territory.
Compliant (Y / N / P) | Enter Y = Yes (compliant), N = No (non-compliant), P = Partial (partially met). Use dropdown where available. Non-compliances must be captured in the Evidence / Notes column and in the Review Summary.
N/A | Mark with a tick or 'N/A' if the item is not applicable to this specific task or SWMS. Provide a brief justification in Evidence / Notes where the reason may not be self-evident.
Evidence / Notes | Record the evidence reviewed (e.g. document reference, observation, verbal confirmation) and any relevant notes. For non-compliances, describe what is missing or inadequate and what corrective action is required.
Review Summary | Complete the summary section after reviewing all items. Record overall rating, count of non-compliances, corrective actions required and final approval decision.
Copyright Notice | This checklist is the intellectual property of MiSAFE Solutions Pty Ltd. It must not be reproduced, distributed or modified without written permission.
© Copyright MiSAFE Solutions Pty Ltd ¦ MISAFE-IMS-TMP-022-V1.0 ¦ Uncontrolled When Printed