## Specificity Audit Checklist
SWMS Specificity Audit Checklist
A one-page audit tool for reviewers to confirm a SWMS is specific to the task, site, plant, materials, PPE, emergency response, personnel and consultation evidence before approval.
SWMS Doc ID: |  | SWMS Title: |  |  | Project / Site: |  |  | Audit Date:
Auditor Name: |  | Auditor Role: |  |  | SWMS Version: |  |  | Overall Result:
# | Audit Area | Specificity Question | Yes / No / Action | Evidence Reference | Action Required | Action Owner | Due Date | Date Closed | Notes
1 | 1. HRCW Identification | Does the SWMS identify the high risk construction work by reference to the specific Regulation 291 sub-section that applies to this task? |  | WHS Reg 299(1)(a)
2 | 1. HRCW Identification | Does the description of the work include the site, the work area and the sequence rather than a generic activity heading? |  | WHS Reg 299(1)(a)
3 | 2. Task Steps | Is the work broken down into discrete steps that reflect the actual sequence on this site, including handovers between crews and changes of plant? |  | WHS Reg 299(1)(b)
4 | 2. Task Steps | Could a worker who has never seen the site read the steps and know what to do next, in order? |  | WHS Reg 299(1)(b)
5 | 3. Hazards | Are the hazards specific to the site, the materials, the plant and the sequence rather than copied from a generic risk register? |  | WHS Reg 299(1)(b)
6 | 3. Hazards | Are the hazards described in the words the workers on this job actually use to talk about the work? |  | WHS Reg 299(1)(b)
7 | 4. Controls and Hierarchy | Do the controls follow the hierarchy in Regulation 36, with elimination and substitution considered before isolation, engineering, administration and PPE? |  | WHS Reg 36, 299(1)(c)
8 | 4. Controls and Hierarchy | Are the controls anchored to the actual plant, materials, design and personnel on this job, with specific equipment, ratings and procedures named? |  | WHS Reg 299(1)(c)
9 | 5. Plant, Materials and Substances | Are all items of plant, materials and hazardous substances listed by make, model, type or SDS reference rather than generic category? |  | WHS Reg 299(1)(c)
10 | 5. Plant, Materials and Substances | Does every item listed in the SWMS actually appear on site, with no carry-over from previous jobs? |  | WHS Reg 299(1)(c)
11 | 6. PPE Specificity | Is the PPE specified by class, standard and exposure (for example P2 respirator, indirect-vent goggles, Class 5 nitrile gloves) rather than a generic listing? |  | WHS Reg 44, 299(1)(c)
12 | 6. PPE Specificity | Does the PPE listed match the SDS Section 8 requirements for every substance referenced in the SWMS? |  | WHS Reg 44
13 | 7. Emergency Response | Does the emergency response reference the actual evacuation route, muster point and rescue plan for the work being done, with the location of first aid and rescue equipment named? |  | WHS Reg 42, 43
14 | 7. Emergency Response | Are the emergency contacts current, named and reachable on the day the work is being done? |  | WHS Reg 42
15 | 8. Personnel and Consultation | Are the workers, supervisors and HSR named, with tickets, competencies and roles in the sequence recorded? |  | WHS Act s.19(3)(f); Reg 300
16 | 8. Personnel and Consultation | Is there documentary evidence that the workers carrying out the work were consulted on this version of the SWMS before it was approved? |  | WHS Act s.47, s.48; Reg 300
Reviewer Sign-Off
Auditor Signature: |  |  |  |  | Date:

## Failure Patterns
Where Generic SWMS Templates Predictably Fail
# | Failure Pattern | What it Looks Like in a SWMS | Why it Fails | Specificity Fix
1 | Task steps from the textbook | Set up exclusion zone. Install fall protection. Commence work. | Real sequence has 14 steps, 3 handovers, 2 plant changes and a temporary works element the template doesn't cover. | Break the work down into the actual sequence on site, with named plant changes and handovers.
2 | Plant and materials not on site | Uses scissor lift to complete work at height. | Site is using a boom lift on this job, not a scissor lift. The pre-start and operator competencies don't match. | Name each item by make, model, registration and operator, matched to the SWMS revision.
3 | Generic PPE listing | Hard hat, hi-vis, safety glasses, gloves. | Doesn't address P2 respirators for grinding stainless, indirect-vent goggles for acid decant, or full-face shields for hot work. | Specify PPE by class, standard and exposure, anchored to SDS Section 8 for chemicals.
4 | Hazards from the risk register | Slips, trips and falls. Manual handling. | Inspector reading a structural demolition SWMS expects to see fall from height, structural collapse, hazardous dust and live services, not the generic catalogue. | Describe hazards in the words workers use, specific to the site and the sequence.
5 | Emergency response written to template | Call 000. Report to site supervisor. | Doesn't reference the actual evacuation route, muster point, location of first aid or rescue plan for the work being done. | Name the route, the muster point, the first aid and rescue equipment, the people and the means of evacuation.
6 | Personnel as job titles only | Site supervisor. Qualified worker. | Cannot evidence the competence of the people carrying out the work, contrary to s.19(3)(f). | Name workers, supervisors and HSR with tickets, competencies and roles in the sequence.
7 | No consultation evidence | Same signature page as the last 12 SWMS. | Cannot demonstrate s.47 and s.48 consultation. Cannot show workers contributed to this version. | Capture consultation method, attendees, issues raised and decisions taken on a Consultation Record bound to this SWMS revision.
8 | Site-specific information missing | Project name in header is the only site reference. | SWMS could be used on any project. Inspector concludes it wasn't written for this one. | Reference the site, the work area, the work face, the access route and the site rules in the body of the SWMS.