## Subcontractor SWMS Register
SWMS Subcontractor Review and Acceptance Register
Review, accept or reject each subcontractor's SWMS at induction and evidence the principal contractor's duty under the WHS Regulation 2017.
Project / Site: |  | Level 5 Commercial Fit-Out |  | Principal Contractor: | Northline Construction Pty Ltd | WHS Mgmt Plan Ref: |  | WHSMP-2025-014
Project Value: |  | $1.2M (over $250k) |  | Reviewed By: | K. Anderson | Reviewer Role: |  | Site WHS Coordinator
# | Subcontractor (Company) | Trade / Scope of Work | SWMS Doc ID & Rev | HRCW Identified? | Controls Match Site & Task? | Decision | Action Required / Notes | Reviewer | Date
1 | Apex Concreting Pty Ltd | Suspended slab pour | APX-SWMS-07 R3 | Yes | Yes | Accept |  | K. Anderson | 14/07/2025
2 | Voltline Electrical Pty Ltd | Electrical rough-in | VLT-SWMS-02 R1 | Yes | Partial | Revise | SWMS covers live work; revise to de-energised, test before touch, for this scope. | K. Anderson | 14/07/2025
3 | Highpoint Rigging Pty Ltd | Crane lift, steel beams | HPR-SWMS-11 R2 | Yes | Yes | Accept |  | K. Anderson | 14/07/2025
4 | Formset Pty Ltd | Formwork erection | FMS-SWMS-04 R1 | Yes | No | Reject | Generic template; wrong site and plant. Hold formwork until a site-specific SWMS is supplied. | K. Anderson | 15/07/2025
5 | Truecoat Painting Pty Ltd | Spray painting at height | TCP-SWMS-03 R2 | Yes | Yes | Accept |  | K. Anderson | 15/07/2025
6
7
8
9
10
11
12
Review Summary
Subcontractors Reviewed: |  |  | 5 |  | Accepted: |  |  | 3
Needs Revision: |  |  | 1 |  | Rejected: |  |  | 1
Acceptance Gate: |  |  | NOT READY - A subcontractor SWMS was rejected. That work must not start until a compliant SWMS is accepted.
Principal Contractor Sign-Off
Name: |  |  |  | Signature: |  |  |  | Date:
Copyright © MiSAFE Solutions Pty Ltd.

## What a SWMS Review Checks
What a Subcontractor SWMS Review Checks
# | Check | What Good Looks Like | Why It Matters
1 | HRCW correctly identified | The SWMS names each category of high risk construction work it covers (work at height, energised electrical, cranes, and so on). | A SWMS is required for each HRCW under regulation 299. A missing category is an uncontrolled risk hiding in plain sight.
2 | Controls match the site | Each control is physically possible on this site, with this plant, and sits at the right level of the hierarchy of controls. | Generic controls listed in the abstract do not control the actual job.
3 | Site-specific, not generic | The SWMS names the plant, materials and work for this job, not 'any site'. | A SWMS that fits any job was not written for this one (see Week 11).
4 | Revision current | The SWMS revision matches the work being done now and the latest control measures. | An out-of-date SWMS controls the wrong work (see Week 9).
5 | Decision recorded | The reviewer records Accept, Revise or Reject with the date and name. | Evidences the principal contractor's duty under regulations 293 and 309 to 310.
Copyright © MiSAFE Solutions Pty Ltd.

## Disclaimer & Copyright
Disclaimer and Copyright
Disclaimer
This template is a general guide only. It does not constitute legal advice and does not replace the requirement for advice tailored to your specific workplace, plant, materials, personnel, jurisdiction or activity. The user is responsible for ensuring compliance with all applicable Work Health and Safety legislation, regulations, codes of practice and Australian standards. MiSAFE Solutions Pty Ltd accepts no liability for any loss, damage, injury or legal action arising from use of, or reliance on, this template. For tailored advice, contact MiSAFE Solutions at misafesolutions.com.au.
Copyright
Copyright © MiSAFE Solutions Pty Ltd. This template is provided as a free resource and may be used and adapted for internal compliance use within your own organisation. Redistribution, resale or commercial reproduction is prohibited without prior written consent from MiSAFE Solutions.
MiSAFE Solutions Pty Ltd ¦ misafesolutions.com.au