## Scaffold Register
Scaffold Handover, Alteration and Inspection Register
List each scaffold or scaffold zone. Record the handover certificate, then log every inspection on the Inspection Log sheet and every alteration on the Alteration Log sheet. The status gate reads DO NOT ACCESS until the handover is recorded, the 30-day inspection is in date, no alteration is open and no post-event inspection is pending. Sample rows use placeholder names and dates: clear them before use.
Scaffolds listed: |  | 3 | Access permitted: |  | 1 | Do not access: |  | 2 | Alterations open: |  | 1
Scaffold details (enter in the white cells; the grey-headed columns I to L calculate themselves)
Scaffold ID | Location or Zone | Duty Class | Top Platform Height (m) | Handover Certificate No. | Handover Date | Competent Person Who Signed | Post-Event Inspection Pending | Last Inspection (auto) | Next Inspection Due (auto) | Open Alterations (auto) | Status Gate (auto)
S-01 | South elevation perimeter scaffold, levels 1 to 4 | Medium | 14.2 | HC-0412 | 2026-10-05 | J. Smith | No | 2026-10-19 | 2026-11-18 | 0 | ACCESS PERMITTED - handover and inspection in date
S-02 | West stair tower | Light | 9.6 | HC-0413 | 2026-09-10 | A. Jones | No | 2026-10-08 | 2026-11-07 | 1 | DO NOT ACCESS - alteration open, re-handover not signed
S-03 | North loading bay platform | Heavy | 6 | HC-0398 | 2026-09-01 | S. Wilson | No | 2026-09-15 | 2026-10-15 | 0 | DO NOT ACCESS - 30-day inspection overdue
Copyright © MiSAFE Solutions Pty Ltd.
Formulas:
Last Inspection (auto) = IF([Scaffold ID]="","",IF(SUMPRODUCT(MAX(('Inspection Log'!$B5:B64=[Scaffold ID])*'Inspection Log'!$A5:A64))=0,"",SUMPRODUCT(MAX(('Inspection Log'!$B5:B64=[Scaffold ID])*'Inspection Log'!$A5:A64))))
Next Inspection Due (auto) = IF([Last Inspection (auto)]="","",[Last Inspection (auto)]+30)

## Inspection Log
Scaffold Inspection Log
Log every inspection by a competent person: before first use, at least every 30 days, after an incident that could affect stability, after repairs or alteration, and after severe weather. Closed off means nobody accesses the scaffold until a later inspection reopens it.
Inspection Date | Scaffold ID | Trigger | Competent Person | Licence Class | Result | Access Decision | Next Due (auto) | Notes or Defects Found
2026-10-05 | S-01 | Before first use | J. Smith | Advanced | Pass | Open | 2026-11-04 | Handover inspection, all bays complete
2026-10-19 | S-01 | After alteration | J. Smith | Advanced | Pass | Open | 2026-11-18 | Three ties removed and replaced, new certificate HC-0412-B
2026-09-10 | S-02 | Before first use | A. Jones | Intermediate | Pass | Open | 2026-10-10
2026-10-08 | S-02 | 30 day | A. Jones | Intermediate | Defect repaired | Open | 2026-11-07 | Missing toe board at level 3 replaced
2026-09-01 | S-03 | Before first use | S. Wilson | Advanced | Pass | Open | 2026-10-01
2026-09-15 | S-03 | 30 day | S. Wilson | Advanced | Pass | Open | 2026-10-15
Copyright © MiSAFE Solutions Pty Ltd.
Formulas:
Next Due (auto) = IF([Inspection Date]="","",[Inspection Date]+30)

## Alteration Log
Scaffold Alteration Log
Log every request to remove, move or add a scaffold component. Only a licensed scaffolder alters the scaffold. The alteration stays OPEN, and the scaffold stays DO NOT ACCESS on the register, until a competent person re-inspects and a new handover certificate is issued.
Date Requested | Scaffold ID | Requested By | Component Altered | Reason | Licensed Scaffolder | Licence Class | Re-Inspection Date | New Handover Cert No. | Re-Handover Date | Status (auto)
2026-10-19 | S-01 | A. Jones | Tie | Three ties off the south elevation for cladding | J. Smith | Advanced | 2026-10-19 | HC-0412-B | 2026-10-19 | CLOSED
2026-10-19 | S-02 | C. Brown | Plank or deck | Level 2 plank lifted to run a cable | A. Jones | Intermediate |  |  |  | OPEN - do not access
Copyright © MiSAFE Solutions Pty Ltd.

## Rules and Triggers
Scaffold Rules and Inspection Triggers Reference
The rules the register enforces, drawn from the model WHS Regulations and Safe Work Australia guidance. Check your own jurisdiction's regulations and the scaffold designer's instructions, which take precedence.
# | Rule or Trigger | What the SWMS Must State | Reference
1 | SWMS for scaffold work | Scaffold erection, alteration and dismantling is high risk construction work where a person could fall more than 2 m. The SWMS identifies the work, the hazards and the controls, and the crew works in accordance with it. | WHS Regs 291(a), 299 and 300
2 | Written confirmation before use | A scaffold from which a person or object could fall more than 4 m must not be used until a competent person has given written confirmation that construction is complete. The handover certificate is that confirmation. | WHS Reg 225
3 | Inspection triggers | A competent person inspects before use, after an incident that could affect stability, after repairs, and at least every 30 days. Add site triggers: severe wind, heavy rain, impact from plant and any alteration. | WHS Reg 225; SWA Guide to scaffold inspection and maintenance
4 | Unauthorised access | The person with management or control prevents unauthorised access while the scaffold is incomplete or unattended. Tag every access point and remove the ladder from an incomplete lift. | WHS Reg 225
5 | Who alters the scaffold | Only a licensed scaffolder erects, alters or dismantles scaffolding where a person or object could fall more than 4 m. Classes: basic, intermediate and advanced. | WHS Reg 81 and Schedule 3
6 | Alteration, repair or addition | A further inspection is completed and a new handover certificate is issued before use resumes. Treat the old certificate as void until then. | SWA Guide to scaffold inspection and maintenance
7 | Handover certificate contents | Certificate number, supplier and client, site and area handed over, duty classification, working decks, top platform height, bay sizes, design registration number, inspector name, licence number, date and time, client acceptance and the 30-day reminder. | SWA Guide to scaffold inspection and maintenance (Appendix B)
8 | Falls hierarchy and rescue | Complete edge protection is a fall prevention device. A missing guardrail is a stop-work item. The SWMS names how the crew would reach and rescue a person who falls. | WHS Regs 78, 79 and 80
9 | Plant and overhead lines | Manage collisions between powered mobile plant and the scaffold. Record the clearance where the scaffold sits near an overhead electric line. | WHS Regs 214 and 166
10 | Standards and guidance | AS/NZS 1576.1 (scaffolding design), AS/NZS 4576 (guidelines for scaffolding), AS 1577 (scaffold planks), the model Code of Practice Managing the risk of falls at workplaces and the SWA General guide for scaffolds and scaffolding work. | Standards and Safe Work Australia
Copyright © MiSAFE Solutions Pty Ltd.

## Disclaimer & Copyright
Disclaimer
This template is a general guide only. It does not constitute legal advice and does not replace the requirement for advice tailored to your specific workplace, scaffold design, personnel, jurisdiction or activity. The user is responsible for ensuring compliance with all applicable Work Health and Safety legislation, regulations, codes of practice and Australian standards. MiSAFE Solutions Pty Ltd accepts no liability for any loss, damage, injury or legal action arising from use of, or reliance on, this template. For tailored advice, contact MiSAFE Solutions at misafesolutions.com.au.
Copyright
© 2026 MiSAFE Solutions Pty Ltd. All rights reserved. This template is provided as a free resource by MiSAFE Solutions and may be downloaded, copied and adapted by end users for internal compliance use within their own organisation. Redistribution, resale, or commercial reproduction in any form is prohibited without prior written consent from MiSAFE Solutions.
About This Template
Scaffold Handover, Alteration and Inspection Register. Use it alongside a scaffold SWMS prepared under Regulation 299 of the model WHS Regulations. The scaffold designer's instructions, the scaffolder's handover certificate and a competent person's advice always take precedence over anything recorded here. Produced by MiSAFE Solutions Pty Ltd as part of the SWMS Mastery Series. Visit misafesolutions.com.au for the full series and for tailored WHS system support.