## Roof Zone Register
Roofing Fall Protection and Fragile Surface Control Checklist
List each roof zone, then record the roof survey, the control chosen under the falls hierarchy, the edge protection or mesh inspection, the anchor and harness inspection and the rescue plan test. Log every fragile area on the Fragile Surface Log sheet. The status gate reads DO NOT ACCESS ROOF until the survey, the control decision and the rescue plan are all signed. Sample rows use placeholder names and dates: clear them before use.
Roof zones listed: |  | 3 | Access permitted: |  | 1 | Do not access roof: |  | 2 | Unprotected fragile areas: |  | 1
Roof zone details (enter in the white cells; the grey-headed columns M and N calculate themselves)
Roof ID | Roof Zone | Pitch (deg) | Height to Eave (m) | Survey Date | Surveyed By | Fragile Map Ref | Control Chosen for Zone | Edge or Mesh Inspected | Anchor and Harness Inspected | Rescue Plan Tested | Decision Signed By | Unprotected Fragile Areas (auto) | Status Gate (auto)
R-01 | Factory main roof, open field | 4 | 7.5 | 2026-10-26 | J. Smith | MAP-01 | Safety mesh | Yes | N/A | Yes | A. Jones | 0 | ACCESS PERMITTED - survey, decision and rescue signed
R-02 | Factory eaves and gutter line | 4 | 7.5 | 2026-10-26 | J. Smith | MAP-01 | Edge protection | Yes | N/A | No | A. Jones | 0 | DO NOT ACCESS ROOF - rescue plan not tested
R-03 | Office roof with skylights | 15 | 4.2 | 2026-10-27 | S. Wilson | MAP-02 | Work positioning | Yes | Yes | Yes | A. Jones | 1 | DO NOT ACCESS ROOF - unprotected fragile area
Copyright © MiSAFE Solutions Pty Ltd.

## Fragile Surface Log
Fragile Surface Log
Log every skylight, translucent or brittle sheet, opening and weak surface found by the roof survey. Do not test a surface by walking on it. A fragile area stays Unprotected, and the roof stays DO NOT ACCESS on the register, until a cover, mesh, guard or exclusion zone is recorded.
Date Found | Roof ID | Fragile Surface Type | Location on Roof | Found By | Protection Installed | Status (auto) | Checked By | Notes
2026-10-26 | R-01 | Translucent sheet | Six sheets along gridline C, bays 4 to 6 | J. Smith | Safety mesh | Protected | J. Smith | Mesh fixed under sheets before access
2026-10-26 | R-01 | Fibre cement | Whole field, 600 sq m | J. Smith | Safety mesh | Protected | J. Smith | Treat every sheet as fragile
2026-10-27 | R-03 | Skylight | Two domed skylights, north slope | S. Wilson | Rated cover | Protected | S. Wilson | Covers fixed down, not loose
2026-10-27 | R-03 | Opening | Plant penetration near ridge | S. Wilson | None yet | Unprotected |  | Guard to be fitted before access
Copyright © MiSAFE Solutions Pty Ltd.

## Rules and Triggers
Roofing Fall Protection Rules Reference
The rules the checklist enforces, drawn from the model WHS Regulations and Safe Work Australia guidance. Check your own jurisdiction's regulations and the manufacturer's instructions for every system, which take precedence.
# | Rule or Control | What the SWMS Must State | Reference
1 | SWMS for roof work | Roof work is high risk construction work where a person could fall more than 2 m. The SWMS identifies the work, the hazards and the controls, and the crew works in accordance with it. | WHS Regs 291(a), 299 and 300
2 | Manage the risk of a fall | The person conducting the business or undertaking manages the risk of a fall that could injure anyone, including a fall through a fragile surface. | WHS Reg 78; Managing the Risk of Falls at Workplaces Code of Practice
3 | Order of controls | A fall prevention device (edge protection, mesh, cover or guard) comes first, work positioning second and fall arrest last. Record the decision for each roof zone and why a higher control was not practicable. | WHS Reg 79
4 | Emergency and rescue | The SWMS names the rescue method, the equipment, the trained rescuers and who calls it. Test the plan before work starts. A person in a harness needs rescue within minutes. | WHS Reg 80
5 | Roof survey and fragile map | A competent person surveys the roof from a safe position before access, records every fragile area and opening, and posts the map at the access point. Nobody tests a surface by walking on it. | Code of Practice; SWA fragile roof guidance
6 | Temporary edge protection | Name the system, the installer and the inspector. Install to the manufacturer's instructions. A missing section is a stop-work item. | AS/NZS 4994 (temporary edge protection)
7 | Safety mesh and covers | Mesh is fixed to the structure before the sheets go on and covers the whole area. Skylights get fixed covers or guards that carry a person, never loose covers. | AS 4389 (safety mesh); manufacturer's instructions
8 | Harness and anchors | Fall arrest is the last choice. Inspect the harness, lanyard and anchor before use, and match the lanyard length to the fall distance. | AS/NZS 1891 series (harnesses and fall arrest)
9 | Access to the roof | State the access (extended ladder, scaffold stair or lift), who checks it and who stops people using another route. Keep an exclusion zone below the work. | Code of Practice; AS/NZS 1657 (ladders and platforms)
10 | Plant and overhead lines | Control loads over people when a crane or hoist delivers sheets. Record the clearance where the roof sits near an overhead electric line. | WHS Regs 166 and 214
Copyright © MiSAFE Solutions Pty Ltd.

## Disclaimer & Copyright
Disclaimer
This template is a general guide only. It does not constitute legal advice and does not replace the requirement for advice tailored to your specific workplace, roof design, personnel, jurisdiction or activity. The user is responsible for ensuring compliance with all applicable Work Health and Safety legislation, regulations, codes of practice and Australian standards. MiSAFE Solutions Pty Ltd accepts no liability for any loss, damage, injury or legal action arising from use of, or reliance on, this template. For tailored advice, contact MiSAFE Solutions at misafesolutions.com.au.
Copyright
© 2026 MiSAFE Solutions Pty Ltd. All rights reserved. This template is provided as a free resource by MiSAFE Solutions and may be downloaded, copied and adapted by end users for internal compliance use within their own organisation. Redistribution, resale, or commercial reproduction in any form is prohibited without prior written consent from MiSAFE Solutions.
About This Template
Roofing Fall Protection and Fragile Surface Control Checklist. Use it alongside a roofing SWMS prepared under Regulation 299 of the model WHS Regulations. The roof designer's and system manufacturer's instructions, and a competent person's advice, always take precedence over anything recorded here. Produced by MiSAFE Solutions Pty Ltd as part of the SWMS Mastery Series. Visit misafesolutions.com.au for the full series and for tailored WHS system support.